CITY NEW PROGRAMME APPROVAL PROCESS

Step by Step Guide

Stage 1: Strategic Consideration and Resourcing by Schools

Step 1. Proposing Academic consults with their Head of Department [HoD] and School Chief Operating Officer [COO] with new programme idea.

Step 2. Proposing Academic writes Market Insight request form, to include basic summary of reasons for programme and School understanding of the market. Draft form template found here.

Market Insight request form is signed off by School Dean and COO before being submitted to the Strategy, Planning and Performance Unit [SPPU].

SPPU Key contact: Andrew Warburton (Andrew.Warburton.1@city.ac.uk)

SPPU Supporting Contact: Christine Giroux (C.Giroux@city.ac.uk)

Step 3. SPPU receives request form, confirms approval has been given by School, and undergoes sector analysis.

Market research is estimated to take three (3) weeks, however, key dates for consideration are available in the Programme Approval guidance. If submitting a market request form during these periods, it may take slightly longer. it may take slightly longer.

Step 4. SPPU will share findings from market research, including sector analysis and recommendations on strategic alignment with proposing Academic.

Step 5. Proposing Academic uses the findings from the Market Insight report to complete the Expression of Interest (EOI) form and draft programme specification, detailing the proposed programme. Form template can be found here. .

Step 6. Proposing Academic submits documentation and Market Insight report to School Programme Review Committee [SPRC] Secretary.

Terms of Reference for SPRC, including key objectives, membership and responsibilities can be found here

Step 7. SPRC Secretary shares Programme submission to members of SPRC and convenes a meeting.

Step 8. SPRC convenes to review proposal for new programme, with the School Dean taking responsibility for approval.

If the proposed Programme is approved:

- Proposing Academic moves onto Stage 2 (Programme Design).

- SPRC secretary informs Marketing of successful programme approval and provides details required for level 1 promotion.

- SPRC secretary adds new Programme to five-year plan / internal school programme tracker.

- Marketing can start promoting the new programme, with the caveat, “subject to approval”.

If the proposed Programme is not approved:

Academic submits Market Insight request form to SPPU

Academic writes initial Programme documentation

Academic submits programme documentation to SPRC

SPRC reviews proposed new Programme

Feedback is provided to the proposing Academic for further discussion and potential resubmission.

Stage 2. Programme Development

Step 1. Proposing Academic and School Associate Dean; Education [ADE] organise a project team to be involved in programme and module design, including engaging with City students. The Project Team is chaired by the proposing Academic where or where appropriate this may be another member of the team with agreement of the ADE who will support the programme development.

Terms of Reference for the project team, including key objectives, and membership can be found here. .

Step 2. The project team will agree and work to a clear timeline, which sets out key steps to be taken, responsibilities for steps, and the date by which steps will be completed. This will include regular catch ups of the project team, to support the Project team’s ability to monitor progress and work to date.

The Project Team activity checklist and clearly outlined roles and responsibilities will be available on the Programme at City staff hub page, here.

The timeline should include a provisional date for submission to CPAC, assisting the CPAC Secretary in monitoring the flow of programmes coming for approval.

Step 3. Proposing Academic and other staff in Project team write programme supporting documentation, including:

Revising the draft Programme specification

Module specifications

Space request form

Financial spreadsheet and rationale

Marketing budget spreadsheet

Evidence of student engagement

Assessment Matrix

Templates for the above forms / spreadsheets can be found here..

Step 4. All members of the Project team review final submission for sign off.

Approval and sign off are captured on the City Programme Approval Committee (CPAC) Form, found here. Digital signatures must be provided.

Step 5. The final submission and appendices are reviewed by the school ADE for final sign off of documentation and submission to CPAC Secretary.

Submissions to CPAC must be made three weeks in advance of the next scheduled meeting.

Terms of Reference for CPAC, including key objectives, membership and responsibilities can be found here..

School ADE has final sign off and submits to CPAC

Project team writes proposed Programme information and supporting documentation

Academic and School ADE creates Project Team

Stage 3. City Approval

Step 1. CPAC Secretary receives the proposed new programme submission and confirms all required signatures have been provided along with all supporting documentation.

If all documentation and signatures have been provided:

- CPAC secretary will share the proposed new programme submission to members of CPAC.

If supporting documentation or signatures are missing:

- CPAC Secretary informs submitting ADE for review and resubmission.

Step 2. The next monthly CPAC meeting will review the proposed new programme.

If the new Programme is approved:

- CPAC Secretary updates City Academic Programme tracker.

- CPAC Secretary will pass all relevant information onto key stakeholders such as Timetabling, Marketing, and IT for SITS update etc.

- Marketing can remove caveat for the new Programme, allowing potential students to apply.

All key information can be found on the CPAC form (template found here).

If the new Programme is not approved:

- Feedback is provided to the proposing Academic and School ADE for further discussion, action, and potential resubmission.

Newly approved Programme added to City’s offering

CPAC reviews Programme submission